## PAM Test Cases
Serial No. | Date | Test Suite ID | Test Case ID | Test Case Objective | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Remarks
1 | 08/05/2026 | TS-PAM-AUTH | TC-PAM-001 | Verify a privileged user can successfully log in using valid credentials and MFA. | PAM system is running, 'admin_user_01' exists with password 'P@ssw0rd123!' and TOTP MFA enabled. | 1. Navigate to PAM login page. 2. Enter username 'admin_user_01'. 3. Enter password 'P@ssw0rd123!'. 4. Enter valid TOTP code from authenticator app. 5. Click 'Login'. | Username: admin_user_01, Password: P@ssw0rd123!, TOTP: 123456 (example) | User 'admin_user_01' is successfully logged into the PAM dashboard.
2 | 08/05/2026 | TS-PAM-AUTH | TC-PAM-002 | Verify the system enforces brute force lockout after multiple failed login attempts. | PAM system is running, 'privileged_user_01' exists. Lockout policy configured for 5 failed attempts within 5 minutes. | 1. Navigate to PAM login page. 2. Enter username 'privileged_user_01'. 3. Enter an incorrect password five times in a row. 4. Attempt a sixth login with any password. | Username: privileged_user_01, Incorrect Password: invalid_pass_1 to invalid_pass_5 | After the fifth failed attempt, the system displays a lockout message and prevents further login attempts for 'privileged_user_01' for the specified duration (e.g., 30 minutes).
3 | 08/05/2026 | TS-PAM-AUTH | TC-PAM-003 | Verify the system prevents MFA bypass attempts. | PAM system is running, 'test_user_mfa' exists with MFA enabled. A network proxy/interception tool (e.g., Burp Suite) is configured to intercept traffic. | 1. Navigate to PAM login page. 2. Log in with 'test_user_mfa' username and password. 3. Intercept the MFA verification request. 4. Attempt to manipulate the MFA token (e.g., provide an empty, invalid, or replayed token) in the intercepted request. 5. Forward the modified request. | Username: test_user_mfa, Password: SecurePass123!, Intercepted MFA request with modified/empty/replayed MFA token. | The system detects the MFA bypass attempt, rejects the login, and logs the security event. Access to the PAM dashboard is denied.
4 | 08/05/2026 | TS-PAM-AUTH | TC-PAM-004 | Verify SSO integration (SAML) allows seamless login for an Active Directory user. | PAM is integrated with Active Directory and configured for SAML SSO. 'ad_user_01' exists in AD and is mapped to a PAM role. | 1. Navigate to the PAM login page and select 'Login with SSO'. 2. User is redirected to the IdP (e.g., AD FS, Okta) login page. 3. Enter 'ad_user_01' credentials in the IdP portal. 4. Authenticate with IdP. | AD Username: ad_user_01, AD Password: ADPasswd#1 | User 'ad_user_01' is successfully logged into the PAM dashboard via SSO after IdP authentication.
5 | 08/05/2026 | TS-PAM-AUTH | TC-PAM-005 | Verify that an expired session token cannot be reused to access the system. | PAM system is running. A user 'session_test_user' is logged in, and their session token is captured. Session timeout is set to 1 minute. | 1. Log in as 'session_test_user' and capture the session token (e.g., from browser developer tools). 2. Wait for the session timeout period (e.g., 2 minutes) for the session to expire. 3. Attempt to access a protected PAM resource using the captured expired session token (e.g., via a browser extension or API call). | User: session_test_user, Captured Session Token: [example_expired_token] | The system rejects the request made with the expired session token, displaying an authentication error or prompting for re-authentication.
6 | 08/05/2026 | TS-PAM-AUTH | TC-PAM-006 | Verify adaptive authentication triggers additional MFA when login originates from a high-risk geo-location. | PAM system is configured for adaptive authentication. Geo-location based risk policy is set to trigger additional MFA for logins outside defined trusted regions (e.g., outside 'US'). 'risk_user_01' exists. | 1. Using a VPN/proxy service, set the client's egress IP to a high-risk geo-location (e.g., 'Nigeria'). 2. Navigate to PAM login page. 3. Enter 'risk_user_01' username and password. | Username: risk_user_01, Password: SecurePass123!, Geo-location: Nigeria (via VPN) | After entering initial credentials, the system prompts for an additional MFA step (e.g., an SMS OTP or push notification) due to the high-risk geo-location. Without this, access is denied.
7 | 08/05/2026 | TS-PAM-AUTH | TC-PAM-007 | Verify certificate-based authentication for a privileged user. | PAM system is configured for certificate-based authentication. 'cert_user_01' has a valid client certificate installed in the browser's certificate store and mapped to their PAM account. | 1. Open a web browser configured to use client certificates. 2. Navigate to the PAM login page. 3. Select the option for 'Certificate Login'. 4. Select the valid client certificate for 'cert_user_01' when prompted by the browser. | Client Certificate for cert_user_01, Certificate Common Name (CN): cert_user_01.company.com | User 'cert_user_01' is successfully logged into the PAM dashboard via certificate authentication without requiring a username/password.
8 | 08/05/2026 | TS-PAM-AUTH | TC-PAM-008 | Verify biometric authentication (e.g., Fingerprint) allows successful login. | PAM system supports biometric authentication. 'bio_user_01' has their biometric profile (e.g., fingerprint) enrolled and linked to their PAM account. A device with a functional biometric sensor is available. | 1. Navigate to PAM login page on a biometric-enabled device (e.g., laptop with fingerprint reader). 2. Enter username 'bio_user_01'. 3. Select 'Biometric Login' option. 4. Use the registered fingerprint to authenticate when prompted. | Username: bio_user_01, Biometric input: Registered Fingerprint Scan | User 'bio_user_01' is successfully logged into the PAM dashboard using biometric authentication.
9 | 08/05/2026 | TS-PAM-AUTH | TC-PAM-009 | Verify user is correctly prompted to re-authenticate if MFA device is lost/unavailable during an active session (edge case). | PAM system is running. 'mfa_user_02' is logged in with an active session using TOTP MFA. MFA re-verification policy is enabled for sensitive actions (e.g., viewing a password). | 1. Log in as 'mfa_user_02' using username/password + TOTP. 2. Attempt a sensitive action requiring re-authentication (e.g., viewing a highly critical password in the vault). 3. Simulate loss/unavailability of the MFA device (e.g., try to enter an incorrect TOTP repeatedly or physically remove access to the device). | Username: mfa_user_02, Password: P@ssword#2, TOTP: [correct, then multiple incorrect] | The system prompts for re-authentication and correctly handles the MFA device unavailability, preventing the sensitive action. Depending on policy, it may lock the user out or force a password reset/MFA recovery.
10 | 08/05/2026 | TS-PAM-AUTH | TC-PAM-010 | Verify SSO misconfiguration leads to a controlled error and not an authentication bypass. | PAM is integrated with a SAML IdP. The IdP's metadata in PAM is intentionally misconfigured (e.g., wrong entity ID or expired certificate). | 1. Navigate to the PAM login page and select 'Login with SSO'. 2. User is redirected to the IdP for authentication. 3. Complete IdP authentication successfully. 4. User is redirected back to PAM. | AD Username: ad_user_misconfig, AD Password: ADPasswd#2, Misconfigured SAML metadata. | The PAM system rejects the SAML assertion due to misconfiguration, displaying a clear error message (e.g., 'SAML authentication failed due to invalid signature/entity ID mismatch'), and prevents login. No fallback to local authentication without explicit user action.
11 | 08/05/2026 | TS-PAM-AUTH | TC-PAM-011 | Verify session token revocation upon logout prevents reuse of the token. | User 'revoke_test' is logged in and their session token has been captured. | 1. Log in as 'revoke_test' and capture the session token (e.g., from browser developer tools). 2. Explicitly log out from the PAM system. 3. Attempt to access a protected PAM resource using the captured (now revoked) session token (e.g., via an API call or modifying browser headers). | User: revoke_test, Captured Session Token: [example_valid_token_before_logout] | The system rejects the request made with the revoked session token, indicating that the session is invalid or expired, and prompts for a new login.
12 | 08/05/2026 | TS-PAM-AUTHZ | TC-PAM-012 | Verify Role-Based Access Control (RBAC) correctly grants access to assigned resources. | PAM system is configured with a role 'DB_Admins' assigned to 'rbac_user_01', granting access to 'SQL_Prod_DB' privileged accounts. | 1. Log in as 'rbac_user_01'. 2. Navigate to the Vault section. 3. Attempt to view privileged accounts associated with 'SQL_Prod_DB'. | User: rbac_user_01, Role: DB_Admins, Target: SQL_Prod_DB privileged accounts. | User 'rbac_user_01' can successfully view and manage (e.g., checkout password) the privileged accounts for 'SQL_Prod_DB'.
13 | 08/05/2026 | TS-PAM-AUTHZ | TC-PAM-013 | Verify RBAC correctly restricts access to unassigned resources. | PAM system is configured with a role 'Network_Admins' assigned to 'rbac_user_02', granting access only to network device accounts. 'SQL_Prod_DB' accounts are not assigned to this role. | 1. Log in as 'rbac_user_02'. 2. Navigate to the Vault section. 3. Attempt to search for or view privileged accounts associated with 'SQL_Prod_DB'. | User: rbac_user_02, Role: Network_Admins, Target: SQL_Prod_DB privileged accounts. | User 'rbac_user_02' is denied access to view or manage 'SQL_Prod_DB' privileged accounts. An appropriate 'Access Denied' message is displayed or the accounts are simply not visible.
14 | 08/05/2026 | TS-PAM-AUTHZ | TC-PAM-014 | Verify Just-In-Time (JIT) access is granted only after approval and for the specified duration. | PAM system is configured for JIT access requests. 'dev_user_01' requests JIT access to 'Prod_Web_Server_Admin' account for 1 hour. An approver 'security_mgr_01' exists. | 1. Log in as 'dev_user_01' and submit a JIT access request for 'Prod_Web_Server_Admin' for 1 hour. 2. Log in as 'security_mgr_01' and approve the request. 3. Log in as 'dev_user_01' and attempt to access 'Prod_Web_Server_Admin' immediately after approval. 4. Wait for 1 hour and 5 minutes. 5. Log in as 'dev_user_01' and attempt to access 'Prod_Web_Server_Admin' again. | Requesting User: dev_user_01, Approver: security_mgr_01, Target: Prod_Web_Server_Admin, Duration: 1 hour. | User 'dev_user_01' can access 'Prod_Web_Server_Admin' immediately after approval. After 1 hour and 5 minutes, access is automatically revoked, and 'dev_user_01' is denied further access. All actions are audited.
15 | 08/05/2026 | TS-PAM-AUTHZ | TC-PAM-015 | Verify Just-Enough-Access (JEA) restricts user actions to only necessary permissions. | PAM system configured for JEA. 'support_user_01' has a JEA role for 'Linux_App_Server' allowing only 'sudo systemctl restart apache2' and 'tail -f /var/log/apache2/error.log'. | 1. Log in as 'support_user_01'. 2. Initiate a session to 'Linux_App_Server' through PAM. 3. Attempt to execute 'sudo systemctl restart apache2'. 4. Attempt to execute 'tail -f /var/log/apache2/error.log'. 5. Attempt to execute 'sudo rm -rf /'. | User: support_user_01, Target: Linux_App_Server, Allowed Commands: 'sudo systemctl restart apache2', 'tail -f /var/log/apache2/error.log', Disallowed Command: 'sudo rm -rf /' | Commands 'sudo systemctl restart apache2' and 'tail -f /var/log/apache2/error.log' execute successfully. Command 'sudo rm -rf /' is blocked by PAM, and an audit log entry is created for the denied action.
16 | 08/05/2026 | TS-PAM-AUTHZ | TC-PAM-016 | Verify privilege escalation attempts are detected and prevented by PAM. | PAM system configured with JEA. 'low_priv_user_01' has restricted access to 'Dev_Server_01'. A simulated exploit payload for privilege escalation is prepared. | 1. Log in as 'low_priv_user_01'. 2. Connect to 'Dev_Server_01' through PAM. 3. Execute a command or script known to attempt privilege escalation (e.g., specific 'sudo' misconfiguration exploit, SUID binary exploit, kernel vulnerability exploit). | User: low_priv_user_01, Target: Dev_Server_01, Exploit payload: [Example privilege escalation command] | PAM detects the privilege escalation attempt, blocks the command or terminates the session, and triggers an alert to security administrators. The full attempt is fully audited.
17 | 08/05/2026 | TS-PAM-AUTHZ | TC-PAM-017 | Verify horizontal access (user A accessing user B's vault) is prevented. | PAM system configured with RBAC. 'user_A' has access only to 'server_A_admin' account. 'user_B' has access only to 'server_B_admin' account. These accounts are not shared. | 1. Log in as 'user_A'. 2. Navigate to the Vault section. 3. Attempt to search for or access the 'server_B_admin' account. | User A: user_A, User B's account: server_B_admin | User 'user_A' is unable to view or access 'server_B_admin' account. The system returns 'Access Denied' or simply does not display the account in the search results.
18 | 08/05/2026 | TS-PAM-AUTHZ | TC-PAM-018 | Verify emergency break-glass access grants full, audited access and triggers specific alerts. | PAM system is configured for break-glass access for 'breakglass_user_01' to 'Prod_Emergency_Root' account. Alerts are configured for break-glass usage to go to SOC. | 1. Log in as 'breakglass_user_01'. 2. Initiate a break-glass access request to 'Prod_Emergency_Root', providing a justification (e.g., 'Urgent production outage fix'). 3. System grants immediate access. 4. Perform several critical actions (e.g., modify system configuration, delete files). 5. Log out. | User: breakglass_user_01, Target: Prod_Emergency_Root, Justification: 'Urgent production outage fix' | Access is granted immediately. All actions performed during the session are fully audited and logged with a clear break-glass flag. A real-time alert is triggered and sent to the security operations center (SOC).
19 | 08/05/2026 | TS-PAM-AUTHZ | TC-PAM-019 | Verify misuse of break-glass access (without actual emergency) is detected and flagged. | PAM system configured for break-glass access. 'breakglass_user_02' has break-glass permissions. Anomaly detection and alerting on unusual break-glass usage are enabled. | 1. Log in as 'breakglass_user_02'. 2. Initiate break-glass access to a critical production server account without a valid, pre-approved emergency ticket or a credible emergency reason. 3. Perform non-critical or suspicious actions (e.g., browse non-system directories, check system uptime repeatedly). | User: breakglass_user_02, Target: 'Prod_Critical_DB_Admin', Justification: 'Testing new feature' (invalid for emergency use). | PAM grants access but flags the usage as potentially anomalous based on the weak justification and/or non-critical activity. An alert is triggered for 'suspicious break-glass usage' to the security team for review.
20 | 08/05/2026 | TS-PAM-AUTHZ | TC-PAM-020 | Verify time-bound access automatically revokes privileges after the specified period. | PAM system configured to grant 'temp_user_01' access to 'staging_server_admin' for 30 minutes, starting now. No manual revocation configured. | 1. Log in as 'temp_user_01'. 2. Access 'staging_server_admin' and perform some actions. 3. After 25 minutes (within the allowed period), attempt to access 'staging_server_admin' again. 4. After 35 minutes (outside the allowed period), attempt to access 'staging_server_admin' again. | User: temp_user_01, Target: staging_server_admin, Duration: 30 minutes. | User 'temp_user_01' can access 'staging_server_admin' successfully at 25 minutes. At 35 minutes, access is denied due to automatic revocation. An audit log entry records the revocation.
21 | 08/05/2026 | TS-PAM-AUTHZ | TC-PAM-021 | Verify IP-based access restrictions prevent login from unauthorized IP addresses. | PAM system is configured to restrict access for 'restricted_user_01' to only '192.168.1.10'. The testing client's current IP is '10.0.0.5'. | 1. Navigate to the PAM login page from the client machine with IP '10.0.0.5'. 2. Enter username 'restricted_user_01' and password. 3. Click 'Login'. | User: restricted_user_01, Password: SecurePass123!, Source IP: 10.0.0.5 (unauthorized) | The system denies the login attempt, displaying an 'Access Denied' message due to IP restriction, and logs the unauthorized attempt.
22 | 08/05/2026 | TS-PAM-VAULT | TC-PAM-022 | Verify a privileged account password can be securely stored and encrypted in the vault (AES-256). | PAM system is running. An 'OS_Server_Admin' account entry type is available for configuration. | 1. Log in as 'vault_admin_01'. 2. Navigate to the Vault management section. 3. Add a new privileged account, 'linux_prod_server_root', with a complex password. 4. Save the account. | Account Name: linux_prod_server_root, Password: Compl3xP@ssw0rd!2026 | The password for 'linux_prod_server_root' is successfully stored in the vault, and is confirmed to be encrypted with AES-256 (e.g., by checking backend configuration or encryption status indicator). The password is not viewable in cleartext.
23 | 08/05/2026 | TS-PAM-VAULT | TC-PAM-023 | Verify the password checkout mechanism releases credentials for a limited time and auto-revokes. | PAM system is running. 'vault_user_02' has access to 'web_app_db_user' account. Checkout duration set to 15 minutes. | 1. Log in as 'vault_user_02'. 2. Request to checkout the password for 'web_app_db_user'. 3. Note the displayed password. 4. After 10 minutes, attempt to checkout the password again (should be displayed). 5. After 16 minutes, attempt to checkout the password again. | User: vault_user_02, Target Account: web_app_db_user | Password is displayed for 15 minutes. At 10 minutes, it's still accessible. At 16 minutes, the password is automatically masked or revoked, and a new checkout request is required. An audit log records checkout and expiry.
24 | 08/05/2026 | TS-PAM-VAULT | TC-PAM-024 | Verify auto password rotation successfully updates the password on the target system after checkout expires. | PAM system is running. 'sql_dev_account' is configured for auto-rotation after each checkout expiry. Target SQL server is online and accessible by PAM with appropriate permissions. | 1. Log in as 'dev_team_lead'. 2. Checkout the password for 'sql_dev_account'. 3. Note the password. 4. Wait for the checkout duration to expire (e.g., 5 minutes). 5. Attempt to log in to the SQL server with the noted (old) password. 6. Checkout the password again from PAM and attempt to log in with the new password. | User: dev_team_lead, Target Account: sql_dev_account, Checkout Duration: 5 minutes. | After checkout expiry, PAM successfully connects to the SQL server and rotates the 'sql_dev_account' password. The old password no longer works, and the newly checked-out password successfully logs in. An audit entry confirms successful rotation.
25 | 08/05/2026 | TS-PAM-VAULT | TC-PAM-025 | Verify dual control mechanism requires two approvals for critical account password checkout. | PAM system is running. 'critical_prod_root' account requires dual control for password checkout, with 'app_owner_01' and 'security_officer_01' as mandatory approvers. 'dev_ops_01' requests access. | 1. Log in as 'dev_ops_01' and request password checkout for 'critical_prod_root'. 2. Log in as 'app_owner_01' and approve the request. 3. Log in as 'dev_ops_01' and attempt to checkout password. 4. Log in as 'security_officer_01' and approve the request. 5. Log in as 'dev_ops_01' and attempt to checkout password. | Requesting User: dev_ops_01, Target: critical_prod_root, Approver 1: app_owner_01, Approver 2: security_officer_01. | After the first approval, 'dev_ops_01' cannot checkout the password; it's still pending. After the second approval, 'dev_ops_01' can successfully checkout the password. All approval actions are fully audited.
26 | 08/05/2026 | TS-PAM-VAULT | TC-PAM-026 | Verify password complexity policies are enforced during manual password updates or new account creation. | PAM system has password complexity policy: Min length 14, 1 uppercase, 1 lowercase, 1 number, 1 special character, no reuse of last 5 passwords. | 1. Log in as 'vault_admin_01'. 2. Attempt to add a new privileged account with a password 'password123'. 3. Attempt to add a new privileged account with a password 'Short!1'. 4. Attempt to add a new privileged account with a password 'P@ssw0rd123!'. | Invalid passwords: 'password123', 'Short!1', Valid password: 'P@ssw0rd123!' | Passwords 'password123' and 'Short!1' are rejected with specific error messages explaining the policy violation (e.g., 'Does not meet length requirement', 'Missing special character'). Password 'P@ssw0rd123!' is accepted.
27 | 08/05/2026 | TS-PAM-VAULT | TC-PAM-027 | Verify SSH key management allows secure storage, checkout, and rotation of SSH keys. | PAM system is configured for SSH key management. 'ssh_user_01' has access to 'linux_host_01' via SSH key. Key rotation policy is enabled (e.g., after 30 days or on checkout expiry). | 1. Log in as 'ssh_user_01'. 2. Checkout the SSH private key for 'linux_host_01'. 3. Use the key to establish an SSH connection to 'linux_host_01'. 4. After the configured key validity/checkout duration expires, attempt to connect to 'linux_host_01' with the old key. 5. Checkout the key again from PAM and attempt to connect. | User: ssh_user_01, Target: linux_host_01, SSH Key. | SSH key is successfully checked out and used for connection. After expiry, the SSH key is automatically rotated on 'linux_host_01' and updated in PAM. The old key no longer works. The new key successfully connects. Key management actions are audited.
28 | 08/05/2026 | TS-PAM-VAULT | TC-PAM-028 | Verify PAM prevents password visibility in cleartext in any system logs after storage or checkout. | PAM system is running. Logging levels are configured (e.g., Debug/Verbose). 'test_user_03' checks out a password. | 1. Log in as 'test_user_03'. 2. Checkout the password for 'test_account_01'. 3. Access PAM system logs (e.g., application logs, database logs, syslog server logs if integrated) as an administrator. 4. Search for the cleartext password value. | User: test_user_03, Account: test_account_01, Password: SecureLogP@ss! | The actual password 'SecureLogP@ss!' is NOT found in cleartext in any accessible system logs. Only masked values, encrypted representations, or references should be present.
29 | 08/05/2026 | TS-PAM-VAULT | TC-PAM-029 | Verify auto password rotation failure is gracefully handled and alerted when target system is offline (edge case). | PAM system is running. 'offline_server_admin' account is configured for auto-rotation. The target server for 'offline_server_admin' is intentionally powered off or made unreachable by PAM. | 1. As a PAM administrator, trigger an immediate password rotation for 'offline_server_admin'. 2. Observe the rotation status in the PAM UI. 3. Check for any generated alerts (e.g., email, SIEM). | Target Account: offline_server_admin, Target Server: 10.10.10.5 (offline). | Password rotation fails. PAM updates the status of 'offline_server_admin' to 'Rotation Failed', generates an alert (e.g., email, SIEM) to administrators, and details the reason (e.g., 'Target system unreachable'). The existing password on the target system remains valid (if reachable).
30 | 08/05/2026 | TS-PAM-VAULT | TC-PAM-030 | Verify password history enforcement prevents reuse of the last N passwords. | PAM system is configured with a password history policy: 'Do not reuse last 5 passwords'. 'password_history_user' has access to an account 'test_account_history'. | 1. Log in as 'password_history_user'. 2. Manually change the password for 'test_account_history' five times, using unique but simple passwords (e.g., P@ss1!, P@ss2!, P@ss3!, P@ss4!, P@ss5!). 3. Attempt to change the password back to P@ss1!. | Account: test_account_history, Passwords: P@ss1!, P@ss2!, P@ss3!, P@ss4!, P@ss5! | The attempt to set the password back to P@ss1! is rejected with an error message indicating it violates the password history policy. All previous valid changes are recorded in the history.
31 | 08/05/2026 | TS-PAM-VAULT | TC-PAM-031 | Verify password reconciliation and auto-heal detects and corrects password inconsistencies. | PAM system running. 'reconciliation_account_01' is managed by PAM. The password on the target system for 'reconciliation_account_01' is manually changed without updating PAM. | 1. Log in to the target system as 'reconciliation_account_01' and manually change its password (e.g., to 'ManualChange123'). 2. In PAM, navigate to 'reconciliation_account_01' settings. 3. Trigger a manual password reconciliation. 4. Observe the outcome in the PAM UI and try to access the target. | Account: reconciliation_account_01, PAM-stored password: 'OldPass456!', Manually changed password on target: 'ManualChange123'. | PAM detects the discrepancy. If auto-heal is enabled, PAM automatically updates its stored password to match 'ManualChange123' or generates a new password and updates both PAM and the target system, ensuring consistency. An audit log entry is created for the reconciliation/healing event.
32 | 08/05/2026 | TS-PAM-VAULT | TC-PAM-032 | Verify API key and service account credential storage and secure retrieval via API. | PAM is configured to store API keys. 'api_service_account_01' has an API key stored. An authorized application or script has API access to PAM with appropriate permissions. | 1. As a PAM admin, store a dummy API key for 'api_service_account_01' in the vault. 2. Develop a script or use an API client (e.g., Postman) to programmatically request the API key from PAM using the authorized application's credentials. 3. Verify the retrieved key is correct and securely transmitted (e.g., not exposed in logs/headers). | Account: api_service_account_01, API Key: 'sk-xxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxx', Application client ID/secret for API access. | The API key is securely retrieved by the authorized application through PAM's API. The retrieval is logged in the audit trail. The key is not exposed in cleartext outside of the secure communication channel.
33 | 08/05/2026 | TS-PAM-SESS | TC-PAM-033 | Verify RDP session proxying, recording (video), and keystroke logging. | PAM system running. 'rdp_user_01' has RDP access to 'windows_server_01' through PAM. Session recording is enabled for video and keystrokes. | 1. Log in as 'rdp_user_01'. 2. Initiate an RDP session to 'windows_server_01' via the PAM gateway. 3. Perform various actions: open applications, type in Notepad ('Sensitive info here'), browse files, open command prompt and type 'whoami'. 4. End the session. 5. As a security admin, retrieve and playback the session recording. | User: rdp_user_01, Target: windows_server_01 (RDP). Actions: Open cmd, type 'whoami', open Notepad, type 'Sensitive info here'. | The RDP session is successfully proxied. The session recording (video and keystrokes/commands) is available, accurately shows all actions, and plays back correctly. Keystrokes 'Sensitive info here' and 'whoami' are explicitly logged.
34 | 08/05/2026 | TS-PAM-SESS | TC-PAM-034 | Verify SSH session proxying, command logging, and session termination by admin. | PAM system running. 'ssh_user_02' has SSH access to 'linux_server_02' through PAM. Session recording is enabled. 'security_admin_02' can monitor and terminate sessions. | 1. Log in as 'ssh_user_02'. 2. Initiate an SSH session to 'linux_server_02' via PAM. 3. Execute several commands (e.g., 'ls -la', 'cat /etc/passwd', 'sudo reboot'). 4. As 'security_admin_02' (from a separate login), identify the active session of 'ssh_user_02' and terminate it via the PAM console. 5. As 'ssh_user_02', attempt to execute another command. | User: ssh_user_02, Target: linux_server_02 (SSH), Admin: security_admin_02. Commands: 'ls -la', 'cat /etc/passwd', 'sudo reboot'. | SSH session is proxied. Commands are executed and logged. 'security_admin_02' successfully terminates the session. 'ssh_user_02' loses connection or gets an error message upon attempting further commands. Termination is audited and logs include all commands executed.
35 | 08/05/2026 | TS-PAM-SESS | TC-PAM-035 | Verify live session monitoring by a security admin provides real-time visibility. | PAM system running. 'monitor_user_01' initiates a session to 'target_server_01'. 'security_observer_01' has live monitoring permissions in PAM. | 1. Log in as 'monitor_user_01'. 2. Initiate an RDP or SSH session to 'target_server_01' via PAM. 3. Perform various actions within the session (e.g., open applications, type, navigate directories). 4. Simultaneously, log in as 'security_observer_01' and start live monitoring of 'monitor_user_01''s active session through the PAM monitoring interface. | User: monitor_user_01, Target: target_server_01, Observer: security_observer_01. Actions: run 'ipconfig', open browser. | 'security_observer_01' can see the actions and screen of 'monitor_user_01' in real-time within the PAM monitoring interface. The monitoring action is audited.
36 | 08/05/2026 | TS-PAM-SESS | TC-PAM-036 | Verify session shadowing allows an admin to join an active privileged session. | PAM system running. 'dev_user_03' has an active SSH session to 'prod_web_server_02'. 'admin_shadow_01' has session shadowing permissions. | 1. Log in as 'dev_user_03' and establish an SSH session to 'prod_web_server_02' via PAM. 2. Execute some commands (e.g., 'whoami', 'pwd'). 3. Log in as 'admin_shadow_01' and initiate shadowing on 'dev_user_03''s active session. 4. As 'admin_shadow_01', type a command (e.g., 'echo Hello from Admin'). 5. As 'dev_user_03', observe the session for the output of 'admin_shadow_01''s command. | User: dev_user_03, Target: prod_web_server_02, Admin: admin_shadow_01. Shadowed command: 'echo Hello from Admin'. | 'admin_shadow_01' successfully joins 'dev_user_03''s session. Commands typed by 'admin_shadow_01' appear in 'dev_user_03''s terminal. The shadowing action is audited.
37 | 08/05/2026 | TS-PAM-SESS | TC-PAM-037 | Verify concurrent session limits per user are enforced. | PAM system configured for a maximum of 2 concurrent sessions for 'limited_session_user'. | 1. Log in as 'limited_session_user'. 2. Open an RDP session to 'server_A' via PAM. 3. Open an SSH session to 'server_B' via PAM. 4. Attempt to open a third session (e.g., RDP to 'server_C') via PAM. | User: limited_session_user, Concurrent limit: 2. Targets: server_A, server_B, server_C. | The first two sessions are established successfully. The attempt to open the third session is denied with an error message indicating the concurrent session limit has been reached. An audit log entry is created for the denied attempt.
38 | 08/05/2026 | TS-PAM-SESS | TC-PAM-038 | Verify session timeout on inactivity automatically terminates sessions. | PAM system configured with session timeout on inactivity set to 5 minutes. 'inactive_user_01' is logged in. | 1. Log in as 'inactive_user_01'. 2. Initiate an RDP session to 'test_server_01' via PAM. 3. Do not interact with the session (no mouse, keyboard activity) for 6 minutes. 4. After 6 minutes, attempt to interact with the RDP session. | User: inactive_user_01, Target: test_server_01, Inactivity timeout: 5 minutes. | After 5 minutes of inactivity, the session is automatically terminated. When 'inactive_user_01' attempts to interact at 6 minutes, the RDP session is disconnected, and they are required to re-establish a new session. Termination is audited.
39 | 08/05/2026 | TS-PAM-SESS | TC-PAM-039 | Verify clipboard restriction during privileged sessions prevents data exfiltration. | PAM system configured to restrict clipboard for 'clipboard_test_user' during RDP sessions to 'sensitive_server_01'. | 1. Log in as 'clipboard_test_user'. 2. Initiate an RDP session to 'sensitive_server_01' via PAM. 3. On 'sensitive_server_01', copy sensitive text (e.g., 'SECRET_DATA_123') to the clipboard. 4. On the client machine (local), attempt to paste the copied text into a local application (e.g., Notepad). | User: clipboard_test_user, Target: sensitive_server_01, Text to copy: 'SECRET_DATA_123'. | The clipboard transfer is blocked. When attempting to paste on the client machine, nothing is pasted or only old local clipboard content is pasted. An audit log entry records the clipboard restriction enforcement.
40 | 08/05/2026 | TS-PAM-SESS | TC-PAM-040 | Verify file transfer restrictions block upload/download during privileged sessions. | PAM system configured to restrict file transfer (upload/download) for 'file_transfer_user' during RDP sessions to 'fileserver_01'. | 1. Log in as 'file_transfer_user'. 2. Initiate an RDP session to 'fileserver_01' via PAM. 3. Attempt to drag-and-drop a file from the client machine to 'fileserver_01'. 4. Attempt to drag-and-drop a file from 'fileserver_01' to the client machine. | User: file_transfer_user, Target: fileserver_01, Test file: 'secret_document.txt'. | File transfer attempts (both upload and download) are blocked by PAM. The drag-and-drop action fails or is explicitly denied. An audit log entry records the file transfer restriction enforcement.
41 | 08/05/2026 | TS-PAM-SESS | TC-PAM-041 | Verify a network disconnect during an active privileged session is handled gracefully (edge case). | PAM system running. 'network_test_user' has an active RDP session to 'target_server_02' through PAM. Physical network access for the client machine can be temporarily interrupted. | 1. Log in as 'network_test_user' and establish an RDP session to 'target_server_02' via PAM. 2. Perform some actions within the session. 3. Physically disconnect the client machine's network cable for 10-15 seconds. 4. Reconnect the network cable. 5. Attempt to interact with the RDP session. | User: network_test_user, Target: target_server_02. | The RDP session should either attempt to reconnect automatically (if configured) or be gracefully terminated without data corruption on the target. Upon reconnection, a new session should be required if the previous one was terminated. The disconnection event is audited.
42 | 08/05/2026 | TS-PAM-SESS | TC-PAM-042 | Verify session hijacking mid-stream is detected and prevented. | PAM system running with strong session security. 'hijack_test_user' has an active SSH session to 'dev_server_03' through PAM. A network sniffer/MITM tool is set up to attempt session hijacking (e.g., using stolen session cookies/tokens or TCP sequence prediction). | 1. Log in as 'hijack_test_user' and establish an SSH session to 'dev_server_03' via PAM. 2. Start a session hijacking attempt (e.g., replaying session cookies/tokens, manipulating TCP packets) from another machine while the user is active. 3. Attempt to execute commands from the 'hijacker' machine. | User: hijack_test_user, Target: dev_server_03, Hijacker IP: [attacker_ip_address]. | PAM detects the session hijacking attempt (e.g., due to source IP change, unexpected TCP sequence, invalid authentication data), terminates the original session and the hijacking attempt, and triggers a security alert. The original user may be prompted to re-authenticate.
43 | 08/05/2026 | TS-PAM-SESS | TC-PAM-043 | Verify session recording remains continuous without gaps during high activity. | PAM system running. 'recording_user_01' has RDP access to 'heavy_load_server' with session recording enabled. 'heavy_load_server' has a tool to generate high GUI/CPU activity. | 1. Log in as 'recording_user_01'. 2. Initiate an RDP session to 'heavy_load_server' via PAM. 3. Generate high activity within the RDP session (e.g., rapidly opening/closing applications, performing large file operations, running CPU-intensive tasks using a benchmark tool). 4. End the session. 5. As a security admin, retrieve and playback the session recording. | User: recording_user_01, Target: heavy_load_server. Actions: Rapid application launch, large file copy (5GB), CPU stress test for 2 minutes. | The session recording is continuous and comprehensive, capturing all actions without any noticeable gaps, freezes, or dropped frames/commands, even under high activity. Playback is smooth and accurate.
44 | 08/05/2026 | TS-PAM-AUDIT | TC-PAM-044 | Verify every action performed within PAM (login, checkout, session, config change) is fully audited. | PAM system running. 'audit_user_01' has permissions to perform various actions. 'audit_admin_01' can view audit logs. | 1. Log in as 'audit_user_01'. 2. Checkout a password for 'test_account_audit'. 3. Initiate an SSH session to 'audit_server_01' and execute 'ls'. 4. Change a policy setting (e.g., session timeout from 60 to 30 min). 5. Log out. 6. Log in as 'audit_admin_01' and review the audit logs. | User: audit_user_01, Account: test_account_audit, Target: audit_server_01, Policy change: session timeout from 60 to 30 min. | The audit logs contain detailed entries for: 'audit_user_01' login, password checkout for 'test_account_audit', SSH session initiation, execution of 'ls' command, the policy change action, and 'audit_user_01' logout. Each entry includes who, what, when, from where.
45 | 08/05/2026 | TS-PAM-AUDIT | TC-PAM-045 | Verify audit logs are immutable and cannot be tampered with or deleted by unauthorized users. | PAM system running with 'audit_log_system' local storage. 'unauthorized_user_01' has elevated but not full administrative privileges. An attempt to access underlying storage may also be simulated. | 1. Generate several audit log entries (e.g., logins, password checkouts by 'test_user_mod'). 2. As 'unauthorized_user_01', attempt to delete or modify specific audit log entries through the PAM UI/API (if exposed). 3. As an attacker, attempt to directly access and modify audit log files on the underlying OS/database (if possible via root access). | User: unauthorized_user_01, Log entries for 'test_user_mod', attempts to delete 'login_event_XYZ' or modify timestamp. | All attempts to delete or modify audit log entries (via UI, API, or direct file access) are blocked. The system confirms the immutability of logs. Any unauthorized access attempts on logs are themselves logged.
46 | 08/05/2026 | TS-PAM-AUDIT | TC-PAM-046 | Verify real-time alerts are triggered promptly on suspicious activity (e.g., failed login from new IP). | PAM system configured to alert on '5 failed logins from a new IP in 1 minute'. An alert recipient (e.g., email to 'soc@company.com') is configured. | 1. Using a new, previously un-seen IP address, attempt to log in as 'alert_test_user' with incorrect credentials 5 times within a 1-minute window. 2. Monitor the alert recipient's inbox or integrated SIEM system. | User: alert_test_user, Incorrect Password: FailPass#, New Source IP: 203.0.113.10. | A real-time alert is generated and sent to 'soc@company.com' (or SIEM) within seconds of the fifth failed login. The alert details the user, IP, and nature of the suspicious activity.
47 | 08/05/2026 | TS-PAM-AUDIT | TC-PAM-047 | Verify SIEM integration correctly forwards audit logs to a configured SIEM (e.g., Splunk). | PAM is integrated with Splunk via Syslog/API. 'siem_test_user' performs actions. Splunk instance is running and configured to receive logs from PAM. | 1. Log in as 'siem_test_user'. 2. Checkout a password for 'app_server_dev'. 3. Initiate an SSH session to 'siem_target_server_01' and execute a command like 'uptime'. 4. Log out. 5. Log in to Splunk and search for recent events originating from the PAM source, filtered by 'siem_test_user'. | User: siem_test_user, Account: app_server_dev, Command: 'uptime'. | All audit events generated by 'siem_test_user' (login, checkout, session, command, logout) are successfully forwarded to Splunk and appear in search results within an acceptable delay (e.g., < 30 seconds). The log format is parseable.
48 | 08/05/2026 | TS-PAM-AUDIT | TC-PAM-048 | Verify audit log storage full scenario is handled without data loss and alerts are generated (edge case). | PAM system is configured with limited audit log storage (e.g., 100MB for testing). A mechanism to rapidly generate log data (e.g., automated script) exists. Alerts for 'storage full' are configured. | 1. As PAM admin, reduce the audit log storage capacity to a very small size (e.g., 50MB) for testing. 2. Rapidly generate a large volume of audit logs (e.g., repeatedly log in/out, perform many password checkouts, run automated scripts) using 'log_generator_user'. 3. Continue generating logs until storage should theoretically be full. 4. Check for alerts and verify log continuity. | Large volume of login/logout, password checkout actions by 'log_generator_user'. | When audit log storage becomes full, PAM should: a) Prevent new logins/actions from occurring, or b) buffer logs internally until space is freed/SIEM is available, or c) Overwrite oldest logs (if configured) after alerting. An alert 'Audit Log Storage Full' is triggered. No critical audit events are lost. The system does not crash or become unresponsive.
49 | 08/05/2026 | TS-PAM-AUDIT | TC-PAM-049 | Verify compliance reports (e.g., PCI-DSS) are accurate and include relevant privileged access data. | PAM system has sufficient audit data related to privileged access, session recordings, and password rotations over a reporting period (e.g., last 3 months) to cover PCI-DSS requirements. | 1. Log in as 'compliance_officer_01'. 2. Navigate to the Reports section. 3. Generate a 'PCI-DSS Compliance Report' for the last quarter. 4. Review the generated report for accuracy, completeness, and adherence to PCI-DSS requirements (e.g., MFA usage, unique passwords, audit trails of privileged access, session recording summaries). | Reporting Period: Q1 2026, Report Type: PCI-DSS Compliance Report. | The generated PCI-DSS report accurately reflects all privileged access activities, MFA usage, password changes, and session recording summaries for the specified period, demonstrating compliance with relevant PCI-DSS requirements. All data aligns with raw audit logs.
50 | 08/05/2026 | TS-PAM-AUDIT | TC-PAM-050 | Verify anomaly detection triggers alerts on unusual session behavior. | PAM system with anomaly detection enabled. Baseline behavior for 'normal_admin_user' is established (e.g., logs in from US, typical Linux commands, specific time window). | 1. Log in as 'normal_admin_user' from a previously unseen geo-location (e.g., via VPN to 'China') outside typical working hours. 2. Initiate an SSH session to a critical server. 3. Execute a series of highly unusual or suspicious commands not typical for the user (e.g., 'rm -rf /tmp/*', 'dd if=/dev/urandom of=/dev/sda'). | User: normal_admin_user, Unusual Geo-location: China, Unusual Time: 3:00 AM UTC, Unusual Commands: 'rm -rf /tmp/*', 'dd if=/dev/urandom of=/dev/sda'. | Anomaly detection identifies the unusual login location, time, and/or command patterns. An alert is triggered (e.g., 'Suspicious Activity Detected for normal_admin_user'), potentially with a risk score, and sent to security staff. The session may be automatically flagged for review or terminated.
51 | 08/05/2026 | TS-PAM-DISC | TC-PAM-051 | Verify automatic discovery successfully identifies privileged accounts across a network segment. | PAM system is configured with a discovery scanner. A network segment (e.g., 10.0.0.0/24) contains several servers with local admin accounts (e.g., 'Administrator', 'root') and service accounts. | 1. Log in as 'discovery_admin_01'. 2. Navigate to the Discovery module. 3. Configure and initiate an on-demand scan for the 10.0.0.0/24 network segment, providing valid discovery credentials (e.g., 'domain_admin_read_only'). 4. Monitor the scan progress and review the results. | Network Segment: 10.0.0.0/24, Discovery Credentials: 'domain_admin_read_only' / 'Pass!123' | The discovery scan completes successfully. PAM identifies and lists all privileged accounts (local admins, service accounts, domain admins) on the servers within the specified segment in the discovery report. Shadow IT accounts are also identified.
52 | 08/05/2026 | TS-PAM-DISC | TC-PAM-052 | Verify auto-onboarding successfully adds discovered accounts to the vault. | PAM system configured for auto-onboarding of discovered privileged accounts. The previous discovery run identified 'unmanaged_local_admin_01' on 'dev_server_05'. | 1. As 'discovery_admin_01', navigate to the Discovery results section. 2. Select 'unmanaged_local_admin_01' and initiate the auto-onboarding process. 3. Verify the account now appears in the PAM vault management section. | Discovered account: unmanaged_local_admin_01 on dev_server_05. | The 'unmanaged_local_admin_01' account is successfully onboarded into the PAM vault, with its password securely stored and, if configured, automatically rotated. An audit entry records the onboarding event.
53 | 08/05/2026 | TS-PAM-DISC | TC-PAM-053 | Verify discovery scan performance and scalability when finding a large number of accounts (edge case). | PAM system deployed on appropriately scaled hardware. A test environment with 10,000+ simulated privileged accounts distributed across many hosts (e.g., 500+ servers). Scheduled discovery scan is configured. | 1. Initiate a discovery scan targeting the large test environment. 2. Monitor system resource utilization (CPU, memory, disk I/O) on the PAM server and discovery scanner. 3. Observe the time taken for the scan to complete. 4. Review the discovery report for completeness and accuracy of the listed accounts. | Target environment: 10,000+ privileged accounts across 500+ hosts, Discovery scan settings: concurrent scans up to 50 hosts. | The discovery scan completes within an acceptable performance window without resource exhaustion, errors, or crashing. All 10,000+ accounts are correctly identified and listed in the discovery report. The PAM system remains responsive during the scan.
54 | 08/05/2026 | TS-PAM-INTEG | TC-PAM-054 | Verify API access for automation successfully allows programmatic password checkout and rotation. | PAM system running. API access enabled and an API client (e.g., Python script) is authorized with appropriate credentials. 'automation_user' has API permissions for 'jenkins_service_account'. | 1. Using an API client (e.g., curl, Python script), call the PAM API to request a password checkout for 'jenkins_service_account'. 2. Verify the password is returned securely (e.g., as part of a JSON response). 3. Programmatically use the retrieved password (e.g., for a Jenkins job to authenticate). 4. Call the PAM API to trigger an immediate password rotation for 'jenkins_service_account'. 5. Verify the password has changed on the target system and in PAM. | User: automation_user, Target Account: jenkins_service_account, API credentials (client ID/secret). | The PAM API successfully returns the password for 'jenkins_service_account'. The programmatic rotation is successful, and the password on the target system and in PAM is updated. All API calls are audited with context.
55 | 08/05/2026 | TS-PAM-INTEG | TC-PAM-055 | Verify ITSM integration (ServiceNow) for access request tickets works end-to-end. | PAM is integrated with ServiceNow. An access request for 'prod_db_admin' account requires a ServiceNow ticket reference. Approver 'manager_01' is configured in PAM and ServiceNow. | 1. Log in as 'dev_user_02'. 2. Initiate an access request for 'prod_db_admin' in PAM, providing a valid ServiceNow ticket ID (e.g., 'ITSM0012345'). 3. As an approver 'manager_01', review the request in PAM. 4. Verify the ServiceNow ticket status can be checked or linked from within the PAM request details. 5. Approve the request in PAM. 6. Verify the approval status update is reflected in ServiceNow for 'ITSM0012345'. | Requesting User: dev_user_02, Target Account: prod_db_admin, ServiceNow Ticket ID: ITSM0012345. | PAM successfully links the access request to 'ITSM0012345'. The approver can view/verify the ticket details from PAM. Upon approval in PAM, the relevant ServiceNow ticket is updated (e.g., status changed to 'Approved by PAM'). All actions are audited in PAM and ServiceNow.